## Plan
PROM06 Assignment 2 — project plan
Updated 13 Oct 2026, 18:10. Deadline taken as 26 Oct 2026 23:59 from the Canvas export (AB chose not to re-check); target submission 25 Oct. Template formatting follows the template headings held as text. Blue cells editable; summary counts are formulas.
# | Phase | Milestone | Deliverable | Start | Finish | Owner | Status | Notes
1 | Evidence | Source review + repository | Project memory, source docs 00–12 | 2026-10-13 | 2026-10-13 | Claude | Done
2 | Evidence | Independent reruns TC01–TC12 (3 runs each) | PRs #70–#81, 37 runs, artefacts | 2026-10-13 | 2026-10-13 | Claude + AB | Done | AB downloaded artefacts
3 | Evidence | Verified results matrix + decisions D2–D11 | Results workbook: Verified Matrix, Decisions & Caveats | 2026-10-13 | 2026-10-13 | Claude + AB | Done | Decisions agreed by AB
4 | Evidence | TC13–TC15 added and verified | Ground truth (commit cbda52c), PRs #82–#84, 9 runs | 2026-10-13 | 2026-10-13 | Claude + AB | Done
5 | Evidence | AI quality scoring (46 runs) | AI Quality Scoring, Scoring Rules, Inter-rater Check sheets | 2026-10-13 | 2026-10-15 | Claude + AB | Done | Single-rater (AI assistant); no inter-rater check — AB decision 13 Oct
6 | Evidence | Metrics, timing, remediation validation | Metrics, Timing, Remediation Validation sheets; PRs #85–#100 | 2026-10-13 | 2026-10-13 | Claude | Done
7 | Evidence | Evidence register + figures | Evidence Register (36 claims), 6 figures at 300 dpi | 2026-10-13 | 2026-10-13 | Claude | Done
8 | Dissertation | Ch3 Practical Research Methodology (2,100 words) | Chapter 3 draft | 2026-10-13 | 2026-10-14 | Claude | Done | Draft v1 delivered 13 Oct (2,197 words); awaiting AB review; ethics/AI declaration placeholder
9 | Dissertation | Ch4 Analysis of Results (2,500 words) | Chapter 4 draft with tables/figures | 2026-10-15 | 2026-10-16 | Claude | In progress | Draft v1 delivered 13 Oct (2,250 words); inter-rater paragraph pending AB scores
10 | Dissertation | Ch2 Literature Review (2,700 words) | Chapter 2 draft (from A1 review) | 2026-10-17 | 2026-10-17 | Claude | Done | Draft v1 delivered 13 Oct (2,411 words); A1 citation errors corrected; reference details to finalise in audit
11 | Dissertation | Ch5 Project Evaluation and Reflection (1,100 words) | Chapter 5 draft | 2026-10-19 | 2026-10-19 | Claude + AB | In progress | Draft v1 13 Oct (1,343 words); reflection drafted from project record — AB to edit; one [AB] placeholder
12 | Dissertation | Ch6 (550), Ch1 (800), Abstract (250) | Chapters 6, 1 and abstract | 2026-10-20 | 2026-10-20 | Claude | Done | Drafts v1 13 Oct: Ch6 703, Ch1 795, abstract 233 words; RQ1–RQ4 numbered from A1 wording (AB to confirm)
13 | Dissertation | References + Appendices A–G; full draft to AB | Complete draft in template | 2026-10-21 | 2026-10-21 | Claude | Done | Full document assembled 13 Oct (111 pages, 10,046 words, Appendices A–G); AB placeholders: supervisor, faculty, signature/date, Ch5.4
14 | Dissertation | AB review + revisions | Revised draft | 2026-10-22 | 2026-10-22 | AB + Claude | Next
15 | Presentation | Slides (max 10) + timed script | Slide deck + speaker script (12–13 min) | 2026-10-22 | 2026-10-23 | Claude | Next
16 | Presentation | Record presentation (10–15 min) | MP4/AVI/PPTX recording | 2026-10-24 | 2026-10-24 | AB | To do
17 | QA | Final QA: consistency, references, word count, format, PDF | QA checklist, final PDF | 2026-10-24 | 2026-10-25 | Claude + AB | To do
18 | Submission | Submit dissertation PDF + recording | Turnitin submission | 2026-10-25 | 2026-10-25 | AB | To do | Deadline 26 Oct 23:59 (confirm)
19 | Close-out | Close test PRs #56–#68, #70–#100 unmerged | Clean repository | 2026-10-26 | 2026-10-27 | Claude (AB approval) | To do | After submission
Summary
Milestones |  | 19
Done |  | 11
In progress / next |  | 4
To do |  | 4
Complete (%) |  | 57.89%
Days to target submission (from today) |  | 12

## Deliverables
Submission deliverables
Deliverable | Format | Requirement / content | Due | Status
Dissertation | PDF via Turnitin; official template | 9,000–11,000 words incl. abstract; excludes references, figures, tables, appendices | 2026-10-25 | To do
Recorded presentation | MP4/AVI/PPTX | 10–15 minutes; max 10 slides | 2026-10-25 | To do
Results workbook | XLSX (supporting evidence, appendix E source) | Verified matrix, metrics, scoring, register | 2026-10-13 | Done
Evidence archive | GitHub branch prom06-evidence | Raw artefacts, scans, PR comments, logs, figures, scripts | 2026-10-13 | Done
Figures | PNG, 300 dpi | 6 figures (architecture, detection matrix, rates, AI quality, timing, remediation) | 2026-10-13 | Done
Screenshots | PNG from GitHub | 8 screenshots (S1–S8) | 2026-10-16 | Pending AB

## AB Inputs
Inputs needed from AB
Item | Why it is needed | Needed by | Status
TC13–TC15 artefacts | Verify metadata, confirm results, score runs | 2026-10-13 | Done
terraform validate log (run 38412955313) | Evidence for invalid AI tag fix | 2026-10-13 | Done
Official template (.docx) | Write chapters directly into the template — AB: ignore (13 Oct) | 2026-10-14 | Not needed
Confirm deadline on live Canvas | Schedule depends on it — AB: ignore (13 Oct) | 2026-10-14 | Not needed
Inter-rater scores (10 runs, blind) | AB decided not to score (13 Oct); single-rater scoring disclosed as a limitation | 2026-10-15 | Not needed
8 screenshots (S1–S8) | Figures in Ch4, Appendix F | 2026-10-16 | Pending AB
Reflection bullets | Claude drafts from the documented project record; AB must review and edit so it is his own | 2026-10-18 | In progress
Ethics approval status / reference | AB: formal ethics approval not required (13 Oct) | 2026-10-19 | Done
Original PROM04 proposal file | Appendix A | 2026-10-19 | Pending AB
Confluence fix yes/no | Corrects 'independent' wording and TC11 heading — AB: ignore (13 Oct) |  | Not needed

## Word Budget
Word allocation (agreed 13 Oct 2026)
Section | Target words | Actual words | Difference
Abstract | 250 | 233 | -17
Ch1 Introduction | 800 | 795 | -5
Ch2 Literature Review | 2700 | 2408 | -292
Ch3 Practical Research Methodology | 2100 | 2258 | 158
Ch4 Analysis of Results | 2500 | 2290 | -210
Ch5 Project Evaluation and Reflection | 1100 | 1338 | 238
Ch6 Conclusion and Recommendations | 550 | 703 | 153
Total | 10000 | 10025 | 25
Allowed range 9,000–11,000 (incl. abstract). Fill 'Actual words' as chapters are drafted.